Project Status Report II

Date of Report Issue/Prepared: 08/02/2020

Report Prepared By: Andrew Cobb

Employer/Organization: Joey Corp

| Project Name: Project Team: Period Reporting: Overall Project Health |  |  |
| --- | --- | --- |
|  | Start Date: Jan 20, 2020 | End Date: Feb 02, 2020 |
|  | Green |  |

Summary

Project Status Summary

Basic user interface has been implemented, issues with emulators and project environments hindered progress

| Accomplishments As Planned | Planned but not Accomplished |
| --- | --- |
| Data base initialised | Testing Crud interfaces with DB back end |
| Basic user interface |  |

Upcoming Objectives for Feb 3, 2020, 2020 to Feb 23, 2020

|  |  | Planned Activities/Tasks for Next Period |  |  |
| --- | --- | --- | --- | --- |
| Activity/Task | Assigned To |  | Duration | Date |
| Complete Data with all tables | Andrew Cobb |  | 5 days | Feb 17 |
| Interest testing (Dummy Data) in DB | Andrew Cobb |  | 1 day | Feb 18 |
| Continued testing on multiply devices (android + iOS) | Giuseppe Ragusa |  |  |  |
| Teammates screen fully functioned with crud and communicating with DB | Nga Le |  |  |  |

|  | Milestones for Next Period |  |  |
| --- | --- | --- | --- |
| Milestone (Objective) |  | Assigned To | Delivery Date |
| CRUD operations completed |  | Andrew Cobb |  |

Managing Issues and Risk

| Issues/Problems | Resolution Strategy | Due Date |
| --- | --- | --- |
| Emulators are causing issues testing application | Explore additional methods of testing, work with all team members to create stable production environments |  |

| Upcoming Risks | Risk Ranking (Hi, Med, Low) | Risk Impact (Hi, Med, Low) | Mitigation Strategy |
| --- | --- | --- | --- |
| Project Members varying experience will cause discoordination | Low: Project Members have worked on multiple projects with proper coordination | Med | Communication will be established with all members to coordinate tasks that each member prefers |
| Project Schedule interfered by Education Schedule | High: All Project Members are active participants in education, weekly occurrence | Low | Project Timelines and Task Durations design with education as a factor, includes deadlines to be extended if necessary. |
| Absence of Project Member during meeting | Low: Communication with all members established outside meetings | Low | New Meetup date will be set to accommodate the member, or information from the current meeting will be relayed to the absent member. |
| Project Methodology foreign to project members | Medium: previous experience with other methodologies and requirements. | Med | Previous experience will be used as a tool for development throughout the project |

NOTE: Attach additional sheets if insufficient space available